## Slide 1
Revised engagement approach for draft GTAC
Aug 2017
Dec 2017
Oct 2017
Telecon Q&A session (31 August)
Complete GTAC draft released for consultation and negotiation (10 August)
Stakeholder mark-ups and submissions on revised draft GTAC due (9 October)
Release of revised draft GTAC (11 September)
Sept 2017
Nov 2017
Submission of GTAC to GIC for review (8 December)
Ensure provisions of GTAC are well-understood before inviting mark-ups
Enable further revisions to be made to better achieve intent and eliminate ambiguities
Allow stakeholders to propose improvements and highlight any remaining concerns
Allow time for First Gas to review proposed changes and submissions
Allow stakeholders to review changes made following first round of mark-ups and obtain legal review/mark-ups
Allow time for First Gas to finalise the GTAC before submitting to GIC
Allow stakeholders further opportunity to address any unresolved issues (including issues raised by other parties prior to submission of final GTAC)
Initial run through session (17 August)
2-day workshop (24-25 August)
Workshop on revised draft GTAC (15 September)
Release of second revised draft GTAC (3 November)
Final mark-ups on second revised draft GTAC due (24 November)
Focused sessions on selected topics (21 & 28 September)
Jan 2018
Feb 2018
Mar 2018
* See GIC paper “Proposed approach to GTAC assessment” for further details on this stage
GIC complete review (by 23 March)
Submissions on GIC Preliminary Assessment due (23 February)
GIC releases Preliminary Assessment (22 December)